## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
AYURVEDA |  | 30 | 2021-08-21 | 2021-09-20 | 2021-09-29
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-21 | 2021-08-22 | 2
1.2 | Finish webpage | 2021-08-23 | 2021-08-24 | 2
1.3 | Project Design | 2021-08-25 | 2021-08-27 | 2
2 | Coding
2.1 | Phase 1 | 2021-08-28 | 2021-09-02 | 6
2.2 | Phase 2 | 2021-09-03 | 2021-09-09 | 7
2.3 | Additional Features | 2021-09-10 | 2021-09-13 | 4
3 | Testing
3.1 | Phase 1 Testing | 2021-09-14 | 2021-09-15 | 2
3.2 | Modification /Any changes
3.3 | Phase 2 Testing | 2021-09-16 | 2021-09-17 | 2
3.4 | Modification /Any changes | 2021-09-18 | 2021-09-18 | 1
3.5 | Final Testing | 2021-09-19 | 2021-09-20 | 2
4 | Documentation
4.1 | User Guide | 2021-09-24 | 2021-09-24 | 1
4.2 | Presentation | 2021-09-27 | 2021-09-27 | 1

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Leader
| Member Name | Shubham Shrikrushna Gadhave
| PRN No | 210543181026
| Description | Front-end,Database
2 | Role | Team Member
| Member Name | Ahire Juhi Arun
| PRN No | 210543181003
| Description | Back-end
3 | Role | Team Member
| Member Name | Pooja Pradip Belsare
| PRN No | 210543181073
| Description | Back-end
4 | Role | Team Member
| Member Name | Tausif Bholukha
| PRN No | 210543181112
| Description | Front-end,Database